## checklist
id_question | order | name | id_phase
0 | 1 | Is the stakeholder matrix been created? | 0
1 | 2 | Have the groups/individuals that will have an impact or will be impacted been identified? | 0
2 | 3 | Is every group represented by a physical person ? | 0
3 | 4 | Has the level of impact of the project for every stakeholder been defined? | 0
4 | 5 | When defining alternative solutions (and making the SWOT analysis) has the preferred solution for every stakeholder been indicated? | 0
5 | 6 | Is all input received from the key stakeholders taken into account and reflected in the project charter? | 0
6 | 7 | Have agreements been made regarding the reviewing schedule? | 0
7 | 8 | Has the Project Steering Committee (PSC) been established? | 0
8 | 1 | Kick-off Meeting : have all the key stakeholders been identified? | 1
9 | 2 | Kick-off Meeting : have the invited stakeholders confirmed their presence? | 1
10 | 3 | Kick-off Meeting : has the agenda been sent upfront to the key stakeholders for comments? | 1
11 | 4 | Kick-off Meeting : did you had a chat with the key stakeholders after the meeting? | 1
12 | 5 | Have the key stakeholders agreed on how to monitor and control the project? | 1
13 | 6 | Did you agree with the key stakeholders on the way to communicate (means, frequency, format, level of detail)? | 1
14 | 7 | Did you inform the key stakeholders about the change process and the change log? | 1
15 | 8 | Is the risk appetite of every stakeholder added to the stakeholder matrix? | 1
16 | 9 | Has an agreement been made about the overall quality requirements (audits, KPI, …) with the key stakeholders? | 1
17 | 10 | Have the requirements been reviewed and approved by the key stakeholders? | 1
18 | 11 | Are the stakeholders clearly aware of the desired goals and outputs of the project (clear understanding on their activities and the time needed to perform them)? | 1
19 | 12 | Has the Project Owner (PO) organised a formal announcement to the user groups about the transition and the way it will influence their way of working? | 1
20 | 13 | End of phase : did you verifiy if all the stakeholders remain the same for the next phase? | 1
21 | 14 | End of phase : did you thank the stakeholders that will leave the project? | 1
22 | 1 | Kick-off Meeting : have the key stakeholders confirmed their presence? | 2
23 | 2 | Kick-off Meeting : has the agenda been sent upfront to the key stakeholders for comments? | 2
24 | 3 | End of phase : did you verifiy if all the stakeholders remain the same for the next phase? | 2
25 | 4 | End of phase : did you thank the stakeholders that will leave the project? | 2
26 | 5 | Have all needed acceptances been given by the stakeholders? | 2
27 | 1 | Review meeting : is the Project Owner (PO) present? | 3
28 | 2 | Is the Project Acceptance Note undersigned by the Project Owner (PO)? | 3
29 | 3 | Have all stakeholders been thanked for their contribution to the success of the project? | 3
30 | 4 | Is an event been organised to celebrate the success of the project? | 3
31 | 1 | Delays/budget overruns : have the key stakeholders been informed? | 4
32 | 2 | Delays/budget overruns : has a Project Steering Committee (PSC) been organised? | 4
33 | 3 | Business implementation : have regular updates been given to the Project Owner (PO) and relevant stakeholders? | 4

## Summary
<This checklist should be reviewed and customised (if needed) at the start of each phase.The main purpose of the Stakeholders Checklist is to support the Project Manager (PM) when verifying whether the activities related to the key Stakeholders were performed as planned.>
Stakeholders checklist
Organisation / Department: | <Name of the organisation and department.>
Project Name: | <Name of the project.>
Project Owner: | <Name of the Project Owner.>
Business Manager: | <Name of the Business Manager.>
Solution Provider: | <Name of the Solution Provider.>
Project Manager: | <Name of the Project Manager.>
Reviewer Name: | <Name of the person performing the phase-exit reviews.>
Overall Compliance (%) | 17.5%
Overall Phase-Exit Status: | 0.175
Area | Phase-Exit Status | % of Phase Compliance | Date | Already performed?
Initiating | 70% | 70% | dd/mm/yyyy | Yes
Planning | 0% | 0% | dd/mm/yyyy | No
Executing | 0% | 0% | dd/mm/yyyy | No
Closing | 0% | 0% | dd/mm/yyyy | No
Monitoring | 0% | 0% | dd/mm/yyyy | No
Assessment Key:
0.3 | Major key activities for the phase(s) weren't performed (50% of the key activities or more are still to be completed).
0.7 | Some key activities are still to be completed before the phase(s) can be closed (% of compliance between 51% and 80%).
0.9 | Nearly all the key activities for the phase(s) are complete (more than 80% of the key activities). The decision to move to another phase should be taken considering the relevance / adequacy of the remaining activities to the project and its specificities.
Yes
No

## Initiating
| Initiating Phase Checks |  | Date: | dd/mm/yyyy
% of Phase Compliance |  |  | 70% | 70%
# | Description | Answer | Score | Comments
1 | Is the stakeholder matrix been created? | N/A | - | <Add a justification here.>
2 | Have the groups/individuals that will have an impact or will be impacted been identified? | Yes | 10
3 | Is every group represented by a physical person ? | Yes, Partially | 5 |  | Yes
4 | Has the level of impact of the project for every stakeholder been defined? | Yes | 10 |  | Yes, Partially
5 | When defining alternative solutions (and making the SWOT analysis) has the preferred solution for every stakeholder been indicated? | N/A | - |  | No
6 | Is all input received from the key stakeholders taken into account and reflected in the project charter? | No | 0 |  | N/A
7 | Have agreements been made regarding the reviewing schedule? | N/A | -
8 | Has the Project Steering Committee (PSC) been established? | Yes | 10
| Total score for compliance | 3 | 35

## Planning
| Planning Phase Checks |  | Date: | dd/mm/yyyy
% of Phase Compliance |  |  | 0% | 0%
# | Description | Answer | Score | Comments
1 | Kick-off Meeting : have all the key stakeholders been identified? | No | 0 | <Add here the justification for the answer given.>
2 | Kick-off Meeting : have the invited stakeholders confirmed their presence? | No | 0
3 | Kick-off Meeting : has the agenda been sent upfront to the key stakeholders for comments? | No | 0 |  | Yes
4 | Kick-off Meeting : did you had a chat with the key stakeholders after the meeting? | No | 0 |  | Yes, Partially
5 | Have the key stakeholders agreed on how to monitor and control the project? | No | 0 |  | No
6 | Did you agree with the key stakeholders on the way to communicate (means, frequency, format, level of detail)? | No | 0 |  | N/A
7 | Did you inform the key stakeholders about the change process and the change log? | No | 0
8 | Is the risk appetite of every stakeholder added to the stakeholder matrix? | No | 0
9 | Has an agreement been made about the overall quality requirements (audits, KPI, …) with the key stakeholders? | No | 0
10 | Have the requirements been reviewed and approved by the key stakeholders? | No | 0
11 | Are the stakeholders clearly aware of the desired goals and outputs of the project (clear understanding on their activities and the time needed to perform them)? | No | 0
12 | Has the Project Owner (PO) organised a formal announcement to the user groups about the transition and the way it will influence their way of working? | No | 0
13 | End of phase : did you verifiy if all the stakeholders remain the same for the next phase? | No | 0
14 | End of phase : did you thank the stakeholders that will leave the project? | No | 0
| Total score for compliance | 0 | 0

## Executing
| Executing Phase Checks |  | Date: | dd/mm/yyyy
% of Phase Compliance |  |  | 0% | 0%
# | Description | Answer | Score | Comments
1 | Kick-off Meeting : have the key stakeholders confirmed their presence? | No | 0 | <Add here the justification for the answer given.> | Yes
2 | Kick-off Meeting : has the agenda been sent upfront to the key stakeholders for comments? | No | 0 |  | Yes, Partially
3 | End of phase : did you verifiy if all the stakeholders remain the same for the next phase? | No | 0 |  | No
4 | End of phase : did you thank the stakeholders that will leave the project? | No | 0 |  | N/A
5 | Have all needed acceptances been given by the stakeholders? | No | 0
| Total score for compliance | 0 | 0

## Closing
| Closing Phase Checks |  | Date: | dd/mm/yyyy
% of Phase Compliance |  |  | 0% | 0%
# | Description | Answer | Score | Comments
1 | Review meeting : is the Project Owner (PO) present? | No | 0 | <Add here the justification for the answer given.>
2 | Is the Project Acceptance Note undersigned by the Project Owner (PO)? | No | 0 |  | Yes
3 | Have all stakeholders been thanked for their contribution to the success of the project? | No | 0 |  | Yes, Partially
4 | Is an event been organised to celebrate the success of the project? | No | 0 |  | No
| Total score for compliance | 0 | 0

## Monitoring
| Monitoring Checks |  | Date: | dd/mm/yyyy
% of Compliance |  |  | 0% | 0%
# | Description | Answer | Score | Comments
1 | Delays/budget overruns : have the key stakeholders been informed? | No | 0 | <Add here the justification for the answer given.>
2 | Delays/budget overruns : has a Project Steering Committee (PSC) been organised? | No | 0 |  | Yes
3 | Business implementation : have regular updates been given to the Project Owner (PO) and relevant stakeholders? | No | 0 |  | Yes, Partially
| Total score for compliance | 0 | 0 |  | No
N/A