## Stakeholder Matrix
[11 empty] | Teams |  |  |  |  | PSC |  |  |  |  | PCT + Agile roles | [7 empty] | Other + PST
Organisation | Dept / Unit | Team | Name | Notes | Impact | Appropriate Governance Body (AGB) | Project Steering Committee (PSC) | Project Core Team (PCT) | Project Support Team (PST) | Business Implentation Group (BIG) |  | Project Owner (PO) | Business Manager (BM) | Solution Provider (SP) | Project Manager (PM) | Contractor Project Manager (CPM) | Assistant Project Manager (APM) | Other Team member | Team Coordinator (TeCo) | Product Owner (PrOw) | Architecture Owner (ArOw) | Agile Team Member (ATeM) | Other ….. | User Representative (URs) | User | Other ….. | Project Support Officer (PSO) | Project Quality Assurance (PQA) | Comments | Contact Info (Email - Phone)
Note on A3: Identify all the stakeholders of the project Strakeholders are people (or groups) who can affect or be affected by the activities carried out during a project’s lifecycle and/or by the project’s output(s) and outcome(s). A stakeholder can exert influence over the project and its deliverables.
Note on C3: If needed or relevant
Note on D3: First and Last Name of the stakeholder. One person per Line.
Note on F3: Relevance of the Stakeholder K = Key Contact H = High M = Medium L = Low The term “relevance of the stakeholder” is used to designate a stakeholder that is identified for involvement in specified activities and is included in an appropriate plan.

## Hoja1
Phase | Task | AGB | PSC | PO | BM | BIG | SP | PM | PCT | Phase | Task | Role | Cat
Initiating | Project Initiation Request | I | n.a. | A/S | R | S/C | I | n.a. | n.a. | Initiating | Project Initiation Request | AGB | I
Initiating | Business Case | I | C | A | R | C | S | S | n.a. | Initiating | Project Initiation Request | PSC | n.a.
Initiating | Project Charter | I | A | C | S | C | S | R | C | Initiating | Project Initiation Request | PO | A/S
Planning | Planning Kick-off Meeting | I | A | C | S | C | C | R | C | Initiating | Project Initiation Request | BM | R
Planning | Project Handbook | I | I | A | S | C | I | R | C | Initiating | Project Initiation Request | BIG | S/C
Planning | Project Stakeholder Matrix | I | I | A | S | C | I | R | C | Initiating | Project Initiation Request | SP | I
Planning | Project Work Plan | I | A | C | S/C | C | C | R | S/C | Initiating | Project Initiation Request | PM | n.a.
Planning | Outsourcing Plan | A | C | C | C | I | S | R | I | Initiating | Project Initiation Request | PCT | n.a.
Planning | Deliverables Acceptance Plan | I | A | C | S | I | C | R | C | Initiating | Business Case | AGB | I
Planning | Transition Plan | I | A | C | C | C | C | R | C | Initiating | Business Case | PSC | C
Planning | Business Implementation Plan | I | I | A | R | C | I | S | I | Initiating | Business Case | PO | A
Planning | Management Plans | [8 empty] | Initiating | Business Case | BM | R
Planning | Requirements Management Plan | I | I | A | C | C | I | R | S | Initiating | Business Case | BIG | C
Planning | Project Change Management Plan | I | I | A | C | I | I | R | I | Initiating | Business Case | SP | S
Planning | Risk Management Plan | I | C | A | C | I | I | R | I | Initiating | Business Case | PM | S
Planning | Issue Management Plan | I | I | A | C | C | I | R | C | Initiating | Business Case | PCT | n.a.
Planning | Quality Management Plan | I | A | C | C | C | C | R | C | Initiating | Project Charter | AGB | I
Planning | Communications Management Plan | I | I | A | S | C | I | R | C | Initiating | Project Charter | PSC | A
Executing | Executing Kick-off Meeting | I | A | C | S/C | C | C | R | C | Initiating | Project Charter | PO | C
Executing | Project Coordination | I | I | A | S | I | I | R | I | Initiating | Project Charter | BM | S
Executing | Quality Assurance | I | I | I | S | C | I | A | R | Initiating | Project Charter | BIG | C
Executing | Project Reporting | I | I | A | S/C | I/C | I/C | R | C | Initiating | Project Charter | SP | S
Executing | Information Distribution | I | I | A | C | I | I | R | C | Initiating | Project Charter | PM | R
Monitor & Control | Monitor Project Performance | I | I | A | C | C | I | R | C | Initiating | Project Charter | PCT | C
Monitor & Control | Control Schedule | I | I | A | C | C | I | R | C | Planning | Planning Kick-off Meeting | AGB | I
Monitor & Control | Control Cost | I | I | A | C | C | I | R | C | Planning | Planning Kick-off Meeting | PSC | A
Monitor & Control | Manage Stakeholders | I | I | A | S/C | I | C | R | I | Planning | Planning Kick-off Meeting | PO | C
Monitor & Control | Manage Requirements | I | I | A | C | C | I | R | S | Planning | Planning Kick-off Meeting | BM | S
Monitor & Control | Manage Project Changes | I | C | A | S | I | I | R | C | Planning | Planning Kick-off Meeting | BIG | C
Monitor & Control | Manage Risks | I | C | A | S/C | C | I | R | C | Planning | Planning Kick-off Meeting | SP | C
Monitor & Control | Manage Issues & Decisions | I | I | A | S | C | I | R | C | Planning | Planning Kick-off Meeting | PM | R
Monitor & Control | Manage Quality | I | I | I | S/C | C | A | R | C | Planning | Planning Kick-off Meeting | PCT | C
Monitor & Control | Manage Deliverables Acceptance | I | I | A | S | C | C | R | C | Planning | Project Handbook | AGB | I
Monitor & Control | Manage Business Implementation | I | I | A | R | C | I | S | I | Planning | Project Handbook | PSC | I
Monitor & Control | Manage Transition | I | A | C | C | C | C | R | C | Planning | Project Handbook | PO | A
Monitor & Control | Manage Outsourcing | A | C | C | C | I | S | R | I | Planning | Project Handbook | BM | S
Closing | Project-End Review Meeting | I | A | C | S | C | C | R | C | Planning | Project Handbook | BIG | C
Closing | Project-End Report | I | A | C | S | C | C | R | C | Planning | Project Handbook | SP | I
Closing | Administrative Closure | I | C | A | C | I | C | R | I | Planning | Project Handbook | PM | R
[10 empty] | Planning | Project Handbook | PCT | C
[10 empty] | Planning | Project Stakeholder Matrix | AGB | I
[10 empty] | Planning | Project Stakeholder Matrix | PSC | I
[10 empty] | Planning | Project Stakeholder Matrix | PO | A
[10 empty] | Planning | Project Stakeholder Matrix | BM | S
[10 empty] | Planning | Project Stakeholder Matrix | BIG | C
[10 empty] | Planning | Project Stakeholder Matrix | SP | I
[10 empty] | Planning | Project Stakeholder Matrix | PM | R
[10 empty] | Planning | Project Stakeholder Matrix | PCT | C
[10 empty] | Planning | Project Work Plan | AGB | I
[10 empty] | Planning | Project Work Plan | PSC | A
[10 empty] | Planning | Project Work Plan | PO | C
[10 empty] | Planning | Project Work Plan | BM | S/C
[10 empty] | Planning | Project Work Plan | BIG | C
[10 empty] | Planning | Project Work Plan | SP | C
[10 empty] | Planning | Project Work Plan | PM | R
[10 empty] | Planning | Project Work Plan | PCT | S/C
[10 empty] | Planning | Outsourcing Plan | AGB | A
[10 empty] | Planning | Outsourcing Plan | PSC | C
[10 empty] | Planning | Outsourcing Plan | PO | C
[10 empty] | Planning | Outsourcing Plan | BM | C
[10 empty] | Planning | Outsourcing Plan | BIG | I
[10 empty] | Planning | Outsourcing Plan | SP | S
[10 empty] | Planning | Outsourcing Plan | PM | R
[10 empty] | Planning | Outsourcing Plan | PCT | I
[10 empty] | Planning | Deliverables Acceptance Plan | AGB | I
[10 empty] | Planning | Deliverables Acceptance Plan | PSC | A
[10 empty] | Planning | Deliverables Acceptance Plan | PO | C
[10 empty] | Planning | Deliverables Acceptance Plan | BM | S
[10 empty] | Planning | Deliverables Acceptance Plan | BIG | I
[10 empty] | Planning | Deliverables Acceptance Plan | SP | C
[10 empty] | Planning | Deliverables Acceptance Plan | PM | R
[10 empty] | Planning | Deliverables Acceptance Plan | PCT | C
[10 empty] | Planning | Transition Plan | AGB | I
[10 empty] | Planning | Transition Plan | PSC | A
[10 empty] | Planning | Transition Plan | PO | C
[10 empty] | Planning | Transition Plan | BM | C
[10 empty] | Planning | Transition Plan | BIG | C
[10 empty] | Planning | Transition Plan | SP | C
[10 empty] | Planning | Transition Plan | PM | R
[10 empty] | Planning | Transition Plan | PCT | C
[10 empty] | Planning | Business Implementation Plan | AGB | I
[10 empty] | Planning | Business Implementation Plan | PSC | I
[10 empty] | Planning | Business Implementation Plan | PO | A
[10 empty] | Planning | Business Implementation Plan | BM | R
[10 empty] | Planning | Business Implementation Plan | BIG | C
[10 empty] | Planning | Business Implementation Plan | SP | I
[10 empty] | Planning | Business Implementation Plan | PM | S
[10 empty] | Planning | Business Implementation Plan | PCT | I
[10 empty] | Planning | Requirements Management Plan | AGB | I
[10 empty] | Planning | Requirements Management Plan | PSC | I
[10 empty] | Planning | Requirements Management Plan | PO | A
[10 empty] | Planning | Requirements Management Plan | BM | C
[10 empty] | Planning | Requirements Management Plan | BIG | C
[10 empty] | Planning | Requirements Management Plan | SP | I
[10 empty] | Planning | Requirements Management Plan | PM | R
[10 empty] | Planning | Requirements Management Plan | PCT | S
[10 empty] | Planning | Project Change Management Plan | AGB | I
[10 empty] | Planning | Project Change Management Plan | PSC | I
[10 empty] | Planning | Project Change Management Plan | PO | A
[10 empty] | Planning | Project Change Management Plan | BM | C
[10 empty] | Planning | Project Change Management Plan | BIG | I
[10 empty] | Planning | Project Change Management Plan | SP | I
[10 empty] | Planning | Project Change Management Plan | PM | R
[10 empty] | Planning | Project Change Management Plan | PCT | I
[10 empty] | Planning | Risk Management Plan | AGB | I
[10 empty] | Planning | Risk Management Plan | PSC | C
[10 empty] | Planning | Risk Management Plan | PO | A
[10 empty] | Planning | Risk Management Plan | BM | C
[10 empty] | Planning | Risk Management Plan | BIG | I
[10 empty] | Planning | Risk Management Plan | SP | I
[10 empty] | Planning | Risk Management Plan | PM | R
[10 empty] | Planning | Risk Management Plan | PCT | I
[10 empty] | Planning | Issue Management Plan | AGB | I
[10 empty] | Planning | Issue Management Plan | PSC | I
[10 empty] | Planning | Issue Management Plan | PO | A
[10 empty] | Planning | Issue Management Plan | BM | C
[10 empty] | Planning | Issue Management Plan | BIG | C
[10 empty] | Planning | Issue Management Plan | SP | I
[10 empty] | Planning | Issue Management Plan | PM | R
[10 empty] | Planning | Issue Management Plan | PCT | C
[10 empty] | Planning | Quality Management Plan | AGB | I
[10 empty] | Planning | Quality Management Plan | PSC | A
[10 empty] | Planning | Quality Management Plan | PO | C
[10 empty] | Planning | Quality Management Plan | BM | C
[10 empty] | Planning | Quality Management Plan | BIG | C
[10 empty] | Planning | Quality Management Plan | SP | C
[10 empty] | Planning | Quality Management Plan | PM | R
[10 empty] | Planning | Quality Management Plan | PCT | C
[10 empty] | Planning | Communications Management Plan | AGB | I
[10 empty] | Planning | Communications Management Plan | PSC | I
[10 empty] | Planning | Communications Management Plan | PO | A
[10 empty] | Planning | Communications Management Plan | BM | S
[10 empty] | Planning | Communications Management Plan | BIG | C
[10 empty] | Planning | Communications Management Plan | SP | I
[10 empty] | Planning | Communications Management Plan | PM | R
[10 empty] | Planning | Communications Management Plan | PCT | C
[10 empty] | Executing | Executing Kick-off Meeting | AGB | I
[10 empty] | Executing | Executing Kick-off Meeting | PSC | A
[10 empty] | Executing | Executing Kick-off Meeting | PO | C
[10 empty] | Executing | Executing Kick-off Meeting | BM | S/C
[10 empty] | Executing | Executing Kick-off Meeting | BIG | C
[10 empty] | Executing | Executing Kick-off Meeting | SP | C
[10 empty] | Executing | Executing Kick-off Meeting | PM | R
[10 empty] | Executing | Executing Kick-off Meeting | PCT | C
[10 empty] | Executing | Project Coordination | AGB | I
[10 empty] | Executing | Project Coordination | PSC | I
[10 empty] | Executing | Project Coordination | PO | A
[10 empty] | Executing | Project Coordination | BM | S
[10 empty] | Executing | Project Coordination | BIG | I
[10 empty] | Executing | Project Coordination | SP | I
[10 empty] | Executing | Project Coordination | PM | R
[10 empty] | Executing | Project Coordination | PCT | I
[10 empty] | Executing | Quality Assurance | AGB | I
[10 empty] | Executing | Quality Assurance | PSC | I
[10 empty] | Executing | Quality Assurance | PO | I
[10 empty] | Executing | Quality Assurance | BM | S
[10 empty] | Executing | Quality Assurance | BIG | C
[10 empty] | Executing | Quality Assurance | SP | I
[10 empty] | Executing | Quality Assurance | PM | A
[10 empty] | Executing | Quality Assurance | PCT | R
[10 empty] | Executing | Project Reporting | AGB | I
[10 empty] | Executing | Project Reporting | PSC | I
[10 empty] | Executing | Project Reporting | PO | A
[10 empty] | Executing | Project Reporting | BM | S/C
[10 empty] | Executing | Project Reporting | BIG | I/C
[10 empty] | Executing | Project Reporting | SP | I/C
[10 empty] | Executing | Project Reporting | PM | R
[10 empty] | Executing | Project Reporting | PCT | C
[10 empty] | Executing | Information Distribution | AGB | I
[10 empty] | Executing | Information Distribution | PSC | I
[10 empty] | Executing | Information Distribution | PO | A
[10 empty] | Executing | Information Distribution | BM | C
[10 empty] | Executing | Information Distribution | BIG | I
[10 empty] | Executing | Information Distribution | SP | I
[10 empty] | Executing | Information Distribution | PM | R
[10 empty] | Executing | Information Distribution | PCT | C
[10 empty] | Monitor & Control | Monitor Project Performance | AGB | I
[10 empty] | Monitor & Control | Monitor Project Performance | PSC | I
[10 empty] | Monitor & Control | Monitor Project Performance | PO | A
[10 empty] | Monitor & Control | Monitor Project Performance | BM | C
[10 empty] | Monitor & Control | Monitor Project Performance | BIG | C
[10 empty] | Monitor & Control | Monitor Project Performance | SP | I
[10 empty] | Monitor & Control | Monitor Project Performance | PM | R
[10 empty] | Monitor & Control | Monitor Project Performance | PCT | C
[10 empty] | Monitor & Control | Control Schedule | AGB | I
[10 empty] | Monitor & Control | Control Schedule | PSC | I
[10 empty] | Monitor & Control | Control Schedule | PO | A
[10 empty] | Monitor & Control | Control Schedule | BM | C
[10 empty] | Monitor & Control | Control Schedule | BIG | C
[10 empty] | Monitor & Control | Control Schedule | SP | I
[10 empty] | Monitor & Control | Control Schedule | PM | R
[10 empty] | Monitor & Control | Control Schedule | PCT | C
[10 empty] | Monitor & Control | Control Cost | AGB | I
[10 empty] | Monitor & Control | Control Cost | PSC | I
[10 empty] | Monitor & Control | Control Cost | PO | A
[10 empty] | Monitor & Control | Control Cost | BM | C
[10 empty] | Monitor & Control | Control Cost | BIG | C
[10 empty] | Monitor & Control | Control Cost | SP | I
[10 empty] | Monitor & Control | Control Cost | PM | R
[10 empty] | Monitor & Control | Control Cost | PCT | C
[10 empty] | Monitor & Control | Manage Stakeholders | AGB | I
[10 empty] | Monitor & Control | Manage Stakeholders | PSC | I
[10 empty] | Monitor & Control | Manage Stakeholders | PO | A
[10 empty] | Monitor & Control | Manage Stakeholders | BM | S/C
[10 empty] | Monitor & Control | Manage Stakeholders | BIG | I
[10 empty] | Monitor & Control | Manage Stakeholders | SP | C
[10 empty] | Monitor & Control | Manage Stakeholders | PM | R
[10 empty] | Monitor & Control | Manage Stakeholders | PCT | I
[10 empty] | Monitor & Control | Manage Requirements | AGB | I
[10 empty] | Monitor & Control | Manage Requirements | PSC | I
[10 empty] | Monitor & Control | Manage Requirements | PO | A
[10 empty] | Monitor & Control | Manage Requirements | BM | C
[10 empty] | Monitor & Control | Manage Requirements | BIG | C
[10 empty] | Monitor & Control | Manage Requirements | SP | I
[10 empty] | Monitor & Control | Manage Requirements | PM | R
[10 empty] | Monitor & Control | Manage Requirements | PCT | S
[10 empty] | Monitor & Control | Manage Project Changes | AGB | I
[10 empty] | Monitor & Control | Manage Project Changes | PSC | C
[10 empty] | Monitor & Control | Manage Project Changes | PO | A
[10 empty] | Monitor & Control | Manage Project Changes | BM | S
[10 empty] | Monitor & Control | Manage Project Changes | BIG | I
[10 empty] | Monitor & Control | Manage Project Changes | SP | I
[10 empty] | Monitor & Control | Manage Project Changes | PM | R
[10 empty] | Monitor & Control | Manage Project Changes | PCT | C
[10 empty] | Monitor & Control | Manage Risks | AGB | I
[10 empty] | Monitor & Control | Manage Risks | PSC | C
[10 empty] | Monitor & Control | Manage Risks | PO | A
[10 empty] | Monitor & Control | Manage Risks | BM | S/C
[10 empty] | Monitor & Control | Manage Risks | BIG | C
[10 empty] | Monitor & Control | Manage Risks | SP | I
[10 empty] | Monitor & Control | Manage Risks | PM | R
[10 empty] | Monitor & Control | Manage Risks | PCT | C
[10 empty] | Monitor & Control | Manage Issues & Decisions | AGB | I
[10 empty] | Monitor & Control | Manage Issues & Decisions | PSC | I
[10 empty] | Monitor & Control | Manage Issues & Decisions | PO | A
[10 empty] | Monitor & Control | Manage Issues & Decisions | BM | S
[10 empty] | Monitor & Control | Manage Issues & Decisions | BIG | C
[10 empty] | Monitor & Control | Manage Issues & Decisions | SP | I
[10 empty] | Monitor & Control | Manage Issues & Decisions | PM | R
[10 empty] | Monitor & Control | Manage Issues & Decisions | PCT | C
[10 empty] | Monitor & Control | Manage Quality | AGB | I
[10 empty] | Monitor & Control | Manage Quality | PSC | I
[10 empty] | Monitor & Control | Manage Quality | PO | I
[10 empty] | Monitor & Control | Manage Quality | BM | S/C
[10 empty] | Monitor & Control | Manage Quality | BIG | C
[10 empty] | Monitor & Control | Manage Quality | SP | A
[10 empty] | Monitor & Control | Manage Quality | PM | R
[10 empty] | Monitor & Control | Manage Quality | PCT | C
[10 empty] | Monitor & Control | Manage Deliverables Acceptance | AGB | I
[10 empty] | Monitor & Control | Manage Deliverables Acceptance | PSC | I
[10 empty] | Monitor & Control | Manage Deliverables Acceptance | PO | A
[10 empty] | Monitor & Control | Manage Deliverables Acceptance | BM | S
[10 empty] | Monitor & Control | Manage Deliverables Acceptance | BIG | C
[10 empty] | Monitor & Control | Manage Deliverables Acceptance | SP | C
[10 empty] | Monitor & Control | Manage Deliverables Acceptance | PM | R
[10 empty] | Monitor & Control | Manage Deliverables Acceptance | PCT | C
[10 empty] | Monitor & Control | Manage Business Implementation | AGB | I
[10 empty] | Monitor & Control | Manage Business Implementation | PSC | I
[10 empty] | Monitor & Control | Manage Business Implementation | PO | A
[10 empty] | Monitor & Control | Manage Business Implementation | BM | R
[10 empty] | Monitor & Control | Manage Business Implementation | BIG | C
[10 empty] | Monitor & Control | Manage Business Implementation | SP | I
[10 empty] | Monitor & Control | Manage Business Implementation | PM | S
[10 empty] | Monitor & Control | Manage Business Implementation | PCT | I
[10 empty] | Monitor & Control | Manage Transition | AGB | I
[10 empty] | Monitor & Control | Manage Transition | PSC | A
[10 empty] | Monitor & Control | Manage Transition | PO | C
[10 empty] | Monitor & Control | Manage Transition | BM | C
[10 empty] | Monitor & Control | Manage Transition | BIG | C
[10 empty] | Monitor & Control | Manage Transition | SP | C
[10 empty] | Monitor & Control | Manage Transition | PM | R
[10 empty] | Monitor & Control | Manage Transition | PCT | C
[10 empty] | Monitor & Control | Manage Outsourcing | AGB | A
[10 empty] | Monitor & Control | Manage Outsourcing | PSC | C
[10 empty] | Monitor & Control | Manage Outsourcing | PO | C
[10 empty] | Monitor & Control | Manage Outsourcing | BM | C
[10 empty] | Monitor & Control | Manage Outsourcing | BIG | I
[10 empty] | Monitor & Control | Manage Outsourcing | SP | S
[10 empty] | Monitor & Control | Manage Outsourcing | PM | R
[10 empty] | Monitor & Control | Manage Outsourcing | PCT | I
[10 empty] | Closing | Project-End Review Meeting | AGB | I
[10 empty] | Closing | Project-End Review Meeting | PSC | A
[10 empty] | Closing | Project-End Review Meeting | PO | C
[10 empty] | Closing | Project-End Review Meeting | BM | S
[10 empty] | Closing | Project-End Review Meeting | BIG | C
[10 empty] | Closing | Project-End Review Meeting | SP | C
[10 empty] | Closing | Project-End Review Meeting | PM | R
[10 empty] | Closing | Project-End Review Meeting | PCT | C
[10 empty] | Closing | Project-End Report | AGB | I
[10 empty] | Closing | Project-End Report | PSC | A
[10 empty] | Closing | Project-End Report | PO | C
[10 empty] | Closing | Project-End Report | BM | S
[10 empty] | Closing | Project-End Report | BIG | C
[10 empty] | Closing | Project-End Report | SP | C
[10 empty] | Closing | Project-End Report | PM | R
[10 empty] | Closing | Project-End Report | PCT | C
[10 empty] | Closing | Administrative Closure | AGB | I
[10 empty] | Closing | Administrative Closure | PSC | C
[10 empty] | Closing | Administrative Closure | PO | A
[10 empty] | Closing | Administrative Closure | BM | C
[10 empty] | Closing | Administrative Closure | BIG | I
[10 empty] | Closing | Administrative Closure | SP | C
[10 empty] | Closing | Administrative Closure | PM | R
[10 empty] | Closing | Administrative Closure | PCT | I

## <Name of stakeholder>
Key Stakeholder Data Sheet | [6 empty] | < Fill in one sheet for the 3-5 most important stakeholders of your project. Keep the gathered information private >
Personal information | [7 empty] | Involvement during phases
Last name | [7 empty] | Phase | Value | Low | High | 0
First name | [7 empty] | Initiating |  |  |  | 1
Role | [7 empty] | Planning |  |  |  | 2
Mobile | [7 empty] | Executing |  |  |  | 3
Email | [7 empty] | Closing |  |  |  | 4
Internal | [11 empty] | 5
Organisation | [7 empty] | Influence
Dept / Unit | [7 empty] | Topic | Value |  |  | Risk appetite
External | [7 empty] | Power/Influence |  |  |  | Acceptable
Company | [7 empty] | Interest |  |  |  | Deviations acceptable
Address | [11 empty] | Small deviations acceptable
Deviation is not acceptable
Communication preference | [7 empty] | Risk Appetite
Frequency | Face-Face | Text | email | PSR | PSC | Other |  | Area | Level |  |  | Power
Daily | [7 empty] | Budget |  |  |  | Very Important
Weekly | [7 empty] | Timing |  |  |  | Some importance
Bi-monthly | [7 empty] | Scope |  |  |  | Little/no importance
Monthly | [7 empty] | Other
Crisis | [11 empty] | Interest
High
Concerns and needs | [7 empty] | Details |  |  |  | Medium
Low
Influence
Positive
Neutral
Negative

## Project Roles
id_role | name | R/P | Group or individual | role_type | description | PSC_participation | Classification | RASCI
ATeM | Agile Team Member | Provider | Individual | Optional role | Team Member that focuses on producing the actual IS that is part of the project's solution to the stakeholders needs. | No | Agile specific role | 0
APR | Analyst Programmer | Provider | Both | Optional role | Develops the solution according to the specifications | On request | IT specific roles | 0
AGB | Appropriate Governance Body | Requestor | Group | Optional role | Management committee governing a number of projects, mostly at Unit or Department level | On request | Teams | 1
ArOw | Architecture Owner | Provider | Individual | Optional role | The solution architect responsible for the architecture decisions for the Project Core Team (PCT) | No | Agile specific role | 0
APM | Assistant Project Manager | Provider | Individual | Optional role | Assists the Project Manager on project management/Administration activities | On request | Support | 0
BA | Busines analyst | Provider | Group | Optional role | Defines the business requirements for the project | No | Operational role | 0
BIG | Business Implementation Group | Requestor | Group | Key role | They plan and implement the business change activities. | On request | Teams | 1
BM | Business Manager | Requestor | Individual | Key role | Acts on a daily basis on behalf of the Project Owner | Key member | Roles | 1
CO | Consultant | Provider | Individual | Optional role | A person that can give advice regarding specific topics | No | Operational role | 0
CON | Contractor | Provider | Group | Optional role | An external company that is contracted for a specific task(s) | No | Operational role | 0
CPM | Contractor's Project Manager | Provider | Individual | Optional role | Leads the contractor's staff working on the project | On request | Support | 0
DPC | Data Protection Coordinator | Provider | Individual | Optional role | Consults and advises on Data Protection aspects. | On request | Other DG Role | 0
DMO | Document Management Officer | Provider | Individual | Optional role | Assure a coherent implementation of the Document Management Roles. | On request | Other DG Role | 0
FAN | Functional Analyst | Provider | Individual | Optional role | Analyses and describes the requirements | On request | IT specific roles | 0
FA | Functional Architect | Provider | Individual | Optional role | Creates the functional architecture of the solution | On request | IT specific roles | 0
LAM | Leader of Application Mgmt | Provider | Individual | Optional role | Responsible for the delivery of the application | On request | IT specific roles | 0
LSS | Leader of System Support | Provider | Individual | Optional role | Responsible to give support regarding system items | On request | IT specific roles | 0
LISO | Local Information Security Officer | Requestor | Individual | Optional role | Consults and advises on Security aspects. | On request | Other DG Role | 0
PrOw | TeamProduct Owner | Requestor | Individual | Optional role | Represents mainly client and end-users concerns | No | Agile specific role | 0
PCT | Project Core Team | Provider | Group | Key role | They are responsible for the implementation of the project deliverables | On request | Teams | 1
PM | Project Manager | Provider | Individual | Key role | Is responsible for the entire project and its deliverables | Key member | Roles | 1
PO | Project Owner | Requestor | Individual | Key role | The final responsible for the project | Chairman | Roles | 1
PQA | Project Quality Assurance | Provider | Both | Optional role | Responsible for quality assurance and auditing. | On request | Support | 0
PSC | Project Steering Committee | Both | Group | Key decision body | The committee that governs the project made up of PO, BM, PM, SO | Yes | Teams | 1
PSO | Project Support Office | Provider | Group | Optional role | Offers support services to the Project Manager (PM) | On request | Support | 0
PST | Project Support Team | Provider | Group | Optional role | They provide administrative and communications support | On request | Teams | 0
RM | Release Manager | Provider | Individual | Optional role | Plans and supervises every release of the solution | On request | IT specific roles | 0
SP | Solution Provider | Provider | Individual | Key role | Is responsible for providing the solution | Key member | Roles | 1
SU | Support | Provider | Group | Optional role | A group that can support the project (administation, meeting rooms, …) | No | Operational role | 0
TeCo | Team Coordinator | Provider | Individual | Optional role | A facilitator and team coach whose main purpose is to create and maintain the conditions to allow the team to be focused on achieving specific objectives and being successful. | No | Agile specific role | 0
TA | Technical Architect | Provider | Individual | Optional role | Creates the technical architecture of the solution | On request | IT specific roles | 0
US | User | Requestor | Group | Optional role | The group that will use the solution | No | Operational role | 0
Urs | User Representatives | Requestor | Both | Key role | They represent the interests of the users in the project. | On request | Operational role | 0

## Hoja2
id_role | name | description
AGB | Appropriate Governance Body
PSC | Project Steering Committee
PO | Project Owner
BM | Business Manager
BIG | Business Implementation Group
SP | Solution Provider
PM | Project Manager
PCT | Project Core Team