## Stakeholder Matrix
[11 empty] | Teams |  |  |  |  | PSC |  |  |  |  | PCT + Agile roles | [7 empty] | Other + PST
Organisation | Dept / Unit | Team | Name | Notes | Impact | Appropriate Governance Body (AGB) | Project Steering Committee (PSC) | Project Core Team (PCT) | Project Support Team (PST) | Business Implentation Group (BIG) |  | Project Owner (PO) | Business Manager (BM) | Solution Provider (SP) | Project Manager (PM) | Contractor Project Manager (CPM) | Assistant Project Manager (APM) | Other Team member | Team Coordinator (TeCo) | Product Owner (PrOw) | Architecture Owner (ArOw) | Agile Team Member (ATeM) | Other ….. | User Representative (URs) | User | Other ….. | Project Support Officer (PSO) | Project Quality Assurance (PQA) | Comments | Contact Info (Email - Phone)
Note on A3: Identify all the stakeholders of the project Strakeholders are people (or groups) who can affect or be affected by the activities carried out during a project’s lifecycle and/or by the project’s output(s) and outcome(s). A stakeholder can exert influence over the project and its deliverables.
Note on C3: If needed or relevant
Note on D3: First and Last Name of the stakeholder. One person per Line.
Note on F3: Relevance of the Stakeholder K = Key Contact H = High M = Medium L = Low The term “relevance of the stakeholder” is used to designate a stakeholder that is identified for involvement in specified activities and is included in an appropriate plan.

## <Name of stakeholder>
Key Stakeholder Data Sheet | [6 empty] | < Fill in one sheet for the 3-5 most important stakeholders of your project. Keep the gathered information private >
Personal information | [7 empty] | Involvement during phases
Last name | [7 empty] | Phase | Value | Low | High | 0
First name | [7 empty] | Initiating |  |  |  | 1
Role | [7 empty] | Planning |  |  |  | 2
Mobile | [7 empty] | Executing |  |  |  | 3
Email | [7 empty] | Closing |  |  |  | 4
Internal | [11 empty] | 5
Organisation | [7 empty] | Influence
Dept / Unit | [7 empty] | Topic | Value |  |  | Risk appetite
External | [7 empty] | Power/Influence |  |  |  | Acceptable
Company | [7 empty] | Interest |  |  |  | Deviations acceptable
Address | [11 empty] | Small deviations acceptable
Deviation is not acceptable
Communication preference | [7 empty] | Risk Appetite
Frequency | Face-Face | Text | email | PSR | PSC | Other |  | Area | Level |  |  | Power
Daily | [7 empty] | Budget |  |  |  | Very Important
Weekly | [7 empty] | Timing |  |  |  | Some importance
Bi-monthly | [7 empty] | Scope |  |  |  | Little/no importance
Monthly | [7 empty] | Other
Crisis | [11 empty] | Interest
High
Concerns and needs | [7 empty] | Details |  |  |  | Medium
Low
Influence
Positive
Neutral
Negative

## Project Roles
id_role | name | R/P | Group or individual | role_type | description | PSC_participation | Classification | RASCI
ATeM | Agile Team Member | Provider | Individual | Optional role | Team Member that focuses on producing the actual IS that is part of the project's solution to the stakeholders needs. | No | Agile specific role | 0
APR | Analyst Programmer | Provider | Both | Optional role | Develops the solution according to the specifications | On request | IT specific roles | 0
AGB | Appropriate Governance Body | Requestor | Group | Optional role | Management committee governing a number of projects, mostly at Unit or Department level | On request | Teams | 1
ArOw | Architecture Owner | Provider | Individual | Optional role | The solution architect responsible for the architecture decisions for the Project Core Team (PCT) | No | Agile specific role | 0
APM | Assistant Project Manager | Provider | Individual | Optional role | Assists the Project Manager on project management/Administration activities | On request | Support | 0
BA | Busines analyst | Provider | Group | Optional role | Defines the business requirements for the project | No | Operational role | 0
BIG | Business Implementation Group | Requestor | Group | Key role | They plan and implement the business change activities. | On request | Teams | 1
BM | Business Manager | Requestor | Individual | Key role | Acts on a daily basis on behalf of the Project Owner | Key member | Roles | 1
CO | Consultant | Provider | Individual | Optional role | A person that can give advice regarding specific topics | No | Operational role | 0
CON | Contractor | Provider | Group | Optional role | An external company that is contracted for a specific task(s) | No | Operational role | 0
CPM | Contractor's Project Manager | Provider | Individual | Optional role | Leads the contractor's staff working on the project | On request | Support | 0
DPC | Data Protection Coordinator | Provider | Individual | Optional role | Consults and advises on Data Protection aspects. | On request | Other DG Role | 0
DMO | Document Management Officer | Provider | Individual | Optional role | Assure a coherent implementation of the Document Management Roles. | On request | Other DG Role | 0
FAN | Functional Analyst | Provider | Individual | Optional role | Analyses and describes the requirements | On request | IT specific roles | 0
FA | Functional Architect | Provider | Individual | Optional role | Creates the functional architecture of the solution | On request | IT specific roles | 0
LAM | Leader of Application Mgmt | Provider | Individual | Optional role | Responsible for the delivery of the application | On request | IT specific roles | 0
LSS | Leader of System Support | Provider | Individual | Optional role | Responsible to give support regarding system items | On request | IT specific roles | 0
LISO | Local Information Security Officer | Requestor | Individual | Optional role | Consults and advises on Security aspects. | On request | Other DG Role | 0
PrOw | TeamProduct Owner | Requestor | Individual | Optional role | Represents mainly client and end-users concerns | No | Agile specific role | 0
PCT | Project Core Team | Provider | Group | Key role | They are responsible for the implementation of the project deliverables | On request | Teams | 1
PM | Project Manager | Provider | Individual | Key role | Is responsible for the entire project and its deliverables | Key member | Roles | 1
PO | Project Owner | Requestor | Individual | Key role | The final responsible for the project | Chairman | Roles | 1
PQA | Project Quality Assurance | Provider | Both | Optional role | Responsible for quality assurance and auditing. | On request | Support | 0
PSC | Project Steering Committee | Both | Group | Key decision body | The committee that governs the project made up of PO, BM, PM, SO | Yes | Teams | 1
PSO | Project Support Office | Provider | Group | Optional role | Offers support services to the Project Manager (PM) | On request | Support | 0
PST | Project Support Team | Provider | Group | Optional role | They provide administrative and communications support | On request | Teams | 0
RM | Release Manager | Provider | Individual | Optional role | Plans and supervises every release of the solution | On request | IT specific roles | 0
SP | Solution Provider | Provider | Individual | Key role | Is responsible for providing the solution | Key member | Roles | 1
SU | Support | Provider | Group | Optional role | A group that can support the project (administation, meeting rooms, …) | No | Operational role | 0
TeCo | Team Coordinator | Provider | Individual | Optional role | A facilitator and team coach whose main purpose is to create and maintain the conditions to allow the team to be focused on achieving specific objectives and being successful. | No | Agile specific role | 0
TA | Technical Architect | Provider | Individual | Optional role | Creates the technical architecture of the solution | On request | IT specific roles | 0
US | User | Requestor | Group | Optional role | The group that will use the solution | No | Operational role | 0
Urs | User Representatives | Requestor | Both | Key role | They represent the interests of the users in the project. | On request | Operational role | 0

## RASCI_Matrix
Phase | Artefact_Code | Artefact | AGB | PSC | PO | BM | BIG | SP | PM | PCT | Phase | Task | Role | Cat
Initiating | projectInitiationRequest | Project Initiation Request | I | n.a. | A/S | R | S/C | I | n.a. | n.a. | Initiating | Project Initiation Request | AGB | I
Initiating | businessCase | Business Case | I | C | A | R | C | S | S | n.a. | Initiating | Project Initiation Request | PSC | n.a.
Initiating | projectCharter | Project Charter | I | A | C | S | C | S | R | C | Initiating | Project Initiation Request | PO | A/S
Planning | planningKickoffMeeting | Planning Kick-off Meeting | I | A | C | S | C | C | R | C | Initiating | Project Initiation Request | BM | R
Planning | projectHandbook | Project Handbook | I | I | A | S | C | I | R | C | Initiating | Project Initiation Request | BIG | S/C
Planning | projectStakeholderMatrix | Project Stakeholder Matrix | I | I | A | S | C | I | R | C | Initiating | Project Initiation Request | SP | I
Planning | projectWorkPlan | Project Work Plan | I | A | C | S/C | C | C | R | S/C | Initiating | Project Initiation Request | PM | n.a.
Planning | outsourcingPlan | Outsourcing Plan | A | C | C | C | I | S | R | I | Initiating | Project Initiation Request | PCT | n.a.
Planning | deliverablesAcceptancePlan | Deliverables Acceptance Plan | I | A | C | S | I | C | R | C | Initiating | Business Case | AGB | I
Planning | transitionPlan | Transition Plan | I | A | C | C | C | C | R | C | Initiating | Business Case | PSC | C
Planning | businessImplementationPlan | Business Implementation Plan | I | I | A | R | C | I | S | I | Initiating | Business Case | PO | A
Planning | managementPlans | Management Plans | [8 empty] | Initiating | Business Case | BM | R
Planning | requirementsManagementPlan | Requirements Management Plan | I | I | A | C | C | I | R | S | Initiating | Business Case | BIG | C
Planning | projectChangeManagementPlan | Project Change Management Plan | I | I | A | C | I | I | R | I | Initiating | Business Case | SP | S
Planning | riskManagementPlan | Risk Management Plan | I | C | A | C | I | I | R | I | Initiating | Business Case | PM | S
Planning | issueManagementPlan | Issue Management Plan | I | I | A | C | C | I | R | C | Initiating | Business Case | PCT | n.a.
Planning | qualityManagementPlan | Quality Management Plan | I | A | C | C | C | C | R | C | Initiating | Project Charter | AGB | I
Planning | communicationsManagementPlan | Communications Management Plan | I | I | A | S | C | I | R | C | Initiating | Project Charter | PSC | A
Executing | executingKickoffMeeting | Executing Kick-off Meeting | I | A | C | S/C | C | C | R | C | Initiating | Project Charter | PO | C
Executing | projectCoordination | Project Coordination | I | I | A | S | I | I | R | I | Initiating | Project Charter | BM | S
Executing | qualityAssurance | Quality Assurance | I | I | I | S | C | I | A | R | Initiating | Project Charter | BIG | C
Executing | projectReporting | Project Reporting | I | I | A | S/C | I/C | I/C | R | C | Initiating | Project Charter | SP | S
Executing | informationDistribution | Information Distribution | I | I | A | C | I | I | R | C | Initiating | Project Charter | PM | R
Monitor & Control | monitorProjectPerformance | Monitor Project Performance | I | I | A | C | C | I | R | C | Initiating | Project Charter | PCT | C
Monitor & Control | controlSchedule | Control Schedule | I | I | A | C | C | I | R | C | Planning | Planning Kick-off Meeting | AGB | I
Monitor & Control | controlCost | Control Cost | I | I | A | C | C | I | R | C | Planning | Planning Kick-off Meeting | PSC | A
Monitor & Control | manageStakeholders | Manage Stakeholders | I | I | A | S/C | I | C | R | I | Planning | Planning Kick-off Meeting | PO | C
Monitor & Control | manageRequirements | Manage Requirements | I | I | A | C | C | I | R | S | Planning | Planning Kick-off Meeting | BM | S
Monitor & Control | manageProjectChanges | Manage Project Changes | I | C | A | S | I | I | R | C | Planning | Planning Kick-off Meeting | BIG | C
Monitor & Control | manageRisks | Manage Risks | I | C | A | S/C | C | I | R | C | Planning | Planning Kick-off Meeting | SP | C
Monitor & Control | manageIssuesAndDecisions | Manage Issues & Decisions | I | I | A | S | C | I | R | C | Planning | Planning Kick-off Meeting | PM | R
Monitor & Control | manageQuality | Manage Quality | I | I | I | S/C | C | A | R | C | Planning | Planning Kick-off Meeting | PCT | C
Monitor & Control | manageDeliverablesAcceptance | Manage Deliverables Acceptance | I | I | A | S | C | C | R | C | Planning | Project Handbook | AGB | I
Monitor & Control | manageBusinessImplementation | Manage Business Implementation | I | I | A | R | C | I | S | I | Planning | Project Handbook | PSC | I
Monitor & Control | manageTransition | Manage Transition | I | A | C | C | C | C | R | C | Planning | Project Handbook | PO | A
Monitor & Control | manageOutsourcing | Manage Outsourcing | A | C | C | C | I | S | R | I | Planning | Project Handbook | BM | S
Closing | projectEndReviewMeeting | Project-End Review Meeting | I | A | C | S | C | C | R | C | Planning | Project Handbook | BIG | C
Closing | projectEndReport | Project-End Report | I | A | C | S | C | C | R | C | Planning | Project Handbook | SP | I
Closing | administrativeClosure | Administrative Closure | I | C | A | C | I | C | R | I | Planning | Project Handbook | PM | R
[11 empty] | Planning | Project Handbook | PCT | C
[11 empty] | Planning | Project Stakeholder Matrix | AGB | I
[11 empty] | Planning | Project Stakeholder Matrix | PSC | I
[11 empty] | Planning | Project Stakeholder Matrix | PO | A
[11 empty] | Planning | Project Stakeholder Matrix | BM | S
[11 empty] | Planning | Project Stakeholder Matrix | BIG | C
[11 empty] | Planning | Project Stakeholder Matrix | SP | I
[11 empty] | Planning | Project Stakeholder Matrix | PM | R
[11 empty] | Planning | Project Stakeholder Matrix | PCT | C
[11 empty] | Planning | Project Work Plan | AGB | I
[11 empty] | Planning | Project Work Plan | PSC | A
[11 empty] | Planning | Project Work Plan | PO | C
[11 empty] | Planning | Project Work Plan | BM | S/C
[11 empty] | Planning | Project Work Plan | BIG | C
[11 empty] | Planning | Project Work Plan | SP | C
[11 empty] | Planning | Project Work Plan | PM | R
[11 empty] | Planning | Project Work Plan | PCT | S/C
[11 empty] | Planning | Outsourcing Plan | AGB | A
[11 empty] | Planning | Outsourcing Plan | PSC | C
[11 empty] | Planning | Outsourcing Plan | PO | C
[11 empty] | Planning | Outsourcing Plan | BM | C
[11 empty] | Planning | Outsourcing Plan | BIG | I
[11 empty] | Planning | Outsourcing Plan | SP | S
[11 empty] | Planning | Outsourcing Plan | PM | R
[11 empty] | Planning | Outsourcing Plan | PCT | I
[11 empty] | Planning | Deliverables Acceptance Plan | AGB | I
[11 empty] | Planning | Deliverables Acceptance Plan | PSC | A
[11 empty] | Planning | Deliverables Acceptance Plan | PO | C
[11 empty] | Planning | Deliverables Acceptance Plan | BM | S
[11 empty] | Planning | Deliverables Acceptance Plan | BIG | I
[11 empty] | Planning | Deliverables Acceptance Plan | SP | C
[11 empty] | Planning | Deliverables Acceptance Plan | PM | R
[11 empty] | Planning | Deliverables Acceptance Plan | PCT | C
[11 empty] | Planning | Transition Plan | AGB | I
[11 empty] | Planning | Transition Plan | PSC | A
[11 empty] | Planning | Transition Plan | PO | C
[11 empty] | Planning | Transition Plan | BM | C
[11 empty] | Planning | Transition Plan | BIG | C
[11 empty] | Planning | Transition Plan | SP | C
[11 empty] | Planning | Transition Plan | PM | R
[11 empty] | Planning | Transition Plan | PCT | C
[11 empty] | Planning | Business Implementation Plan | AGB | I
[11 empty] | Planning | Business Implementation Plan | PSC | I
[11 empty] | Planning | Business Implementation Plan | PO | A
[11 empty] | Planning | Business Implementation Plan | BM | R
[11 empty] | Planning | Business Implementation Plan | BIG | C
[11 empty] | Planning | Business Implementation Plan | SP | I
[11 empty] | Planning | Business Implementation Plan | PM | S
[11 empty] | Planning | Business Implementation Plan | PCT | I
[11 empty] | Planning | Requirements Management Plan | AGB | I
[11 empty] | Planning | Requirements Management Plan | PSC | I
[11 empty] | Planning | Requirements Management Plan | PO | A
[11 empty] | Planning | Requirements Management Plan | BM | C
[11 empty] | Planning | Requirements Management Plan | BIG | C
[11 empty] | Planning | Requirements Management Plan | SP | I
[11 empty] | Planning | Requirements Management Plan | PM | R
[11 empty] | Planning | Requirements Management Plan | PCT | S
[11 empty] | Planning | Project Change Management Plan | AGB | I
[11 empty] | Planning | Project Change Management Plan | PSC | I
[11 empty] | Planning | Project Change Management Plan | PO | A
[11 empty] | Planning | Project Change Management Plan | BM | C
[11 empty] | Planning | Project Change Management Plan | BIG | I
[11 empty] | Planning | Project Change Management Plan | SP | I
[11 empty] | Planning | Project Change Management Plan | PM | R
[11 empty] | Planning | Project Change Management Plan | PCT | I
[11 empty] | Planning | Risk Management Plan | AGB | I
[11 empty] | Planning | Risk Management Plan | PSC | C
[11 empty] | Planning | Risk Management Plan | PO | A
[11 empty] | Planning | Risk Management Plan | BM | C
[11 empty] | Planning | Risk Management Plan | BIG | I
[11 empty] | Planning | Risk Management Plan | SP | I
[11 empty] | Planning | Risk Management Plan | PM | R
[11 empty] | Planning | Risk Management Plan | PCT | I
[11 empty] | Planning | Issue Management Plan | AGB | I
[11 empty] | Planning | Issue Management Plan | PSC | I
[11 empty] | Planning | Issue Management Plan | PO | A
[11 empty] | Planning | Issue Management Plan | BM | C
[11 empty] | Planning | Issue Management Plan | BIG | C
[11 empty] | Planning | Issue Management Plan | SP | I
[11 empty] | Planning | Issue Management Plan | PM | R
[11 empty] | Planning | Issue Management Plan | PCT | C
[11 empty] | Planning | Quality Management Plan | AGB | I
[11 empty] | Planning | Quality Management Plan | PSC | A
[11 empty] | Planning | Quality Management Plan | PO | C
[11 empty] | Planning | Quality Management Plan | BM | C
[11 empty] | Planning | Quality Management Plan | BIG | C
[11 empty] | Planning | Quality Management Plan | SP | C
[11 empty] | Planning | Quality Management Plan | PM | R
[11 empty] | Planning | Quality Management Plan | PCT | C
[11 empty] | Planning | Communications Management Plan | AGB | I
[11 empty] | Planning | Communications Management Plan | PSC | I
[11 empty] | Planning | Communications Management Plan | PO | A
[11 empty] | Planning | Communications Management Plan | BM | S
[11 empty] | Planning | Communications Management Plan | BIG | C
[11 empty] | Planning | Communications Management Plan | SP | I
[11 empty] | Planning | Communications Management Plan | PM | R
[11 empty] | Planning | Communications Management Plan | PCT | C
[11 empty] | Executing | Executing Kick-off Meeting | AGB | I
[11 empty] | Executing | Executing Kick-off Meeting | PSC | A
[11 empty] | Executing | Executing Kick-off Meeting | PO | C
[11 empty] | Executing | Executing Kick-off Meeting | BM | S/C
[11 empty] | Executing | Executing Kick-off Meeting | BIG | C
[11 empty] | Executing | Executing Kick-off Meeting | SP | C
[11 empty] | Executing | Executing Kick-off Meeting | PM | R
[11 empty] | Executing | Executing Kick-off Meeting | PCT | C
[11 empty] | Executing | Project Coordination | AGB | I
[11 empty] | Executing | Project Coordination | PSC | I
[11 empty] | Executing | Project Coordination | PO | A
[11 empty] | Executing | Project Coordination | BM | S
[11 empty] | Executing | Project Coordination | BIG | I
[11 empty] | Executing | Project Coordination | SP | I
[11 empty] | Executing | Project Coordination | PM | R
[11 empty] | Executing | Project Coordination | PCT | I
[11 empty] | Executing | Quality Assurance | AGB | I
[11 empty] | Executing | Quality Assurance | PSC | I
[11 empty] | Executing | Quality Assurance | PO | I
[11 empty] | Executing | Quality Assurance | BM | S
[11 empty] | Executing | Quality Assurance | BIG | C
[11 empty] | Executing | Quality Assurance | SP | I
[11 empty] | Executing | Quality Assurance | PM | A
[11 empty] | Executing | Quality Assurance | PCT | R
[11 empty] | Executing | Project Reporting | AGB | I
[11 empty] | Executing | Project Reporting | PSC | I
[11 empty] | Executing | Project Reporting | PO | A
[11 empty] | Executing | Project Reporting | BM | S/C
[11 empty] | Executing | Project Reporting | BIG | I/C
[11 empty] | Executing | Project Reporting | SP | I/C
[11 empty] | Executing | Project Reporting | PM | R
[11 empty] | Executing | Project Reporting | PCT | C
[11 empty] | Executing | Information Distribution | AGB | I
[11 empty] | Executing | Information Distribution | PSC | I
[11 empty] | Executing | Information Distribution | PO | A
[11 empty] | Executing | Information Distribution | BM | C
[11 empty] | Executing | Information Distribution | BIG | I
[11 empty] | Executing | Information Distribution | SP | I
[11 empty] | Executing | Information Distribution | PM | R
[11 empty] | Executing | Information Distribution | PCT | C
[11 empty] | Monitor & Control | Monitor Project Performance | AGB | I
[11 empty] | Monitor & Control | Monitor Project Performance | PSC | I
[11 empty] | Monitor & Control | Monitor Project Performance | PO | A
[11 empty] | Monitor & Control | Monitor Project Performance | BM | C
[11 empty] | Monitor & Control | Monitor Project Performance | BIG | C
[11 empty] | Monitor & Control | Monitor Project Performance | SP | I
[11 empty] | Monitor & Control | Monitor Project Performance | PM | R
[11 empty] | Monitor & Control | Monitor Project Performance | PCT | C
[11 empty] | Monitor & Control | Control Schedule | AGB | I
[11 empty] | Monitor & Control | Control Schedule | PSC | I
[11 empty] | Monitor & Control | Control Schedule | PO | A
[11 empty] | Monitor & Control | Control Schedule | BM | C
[11 empty] | Monitor & Control | Control Schedule | BIG | C
[11 empty] | Monitor & Control | Control Schedule | SP | I
[11 empty] | Monitor & Control | Control Schedule | PM | R
[11 empty] | Monitor & Control | Control Schedule | PCT | C
[11 empty] | Monitor & Control | Control Cost | AGB | I
[11 empty] | Monitor & Control | Control Cost | PSC | I
[11 empty] | Monitor & Control | Control Cost | PO | A
[11 empty] | Monitor & Control | Control Cost | BM | C
[11 empty] | Monitor & Control | Control Cost | BIG | C
[11 empty] | Monitor & Control | Control Cost | SP | I
[11 empty] | Monitor & Control | Control Cost | PM | R
[11 empty] | Monitor & Control | Control Cost | PCT | C
[11 empty] | Monitor & Control | Manage Stakeholders | AGB | I
[11 empty] | Monitor & Control | Manage Stakeholders | PSC | I
[11 empty] | Monitor & Control | Manage Stakeholders | PO | A
[11 empty] | Monitor & Control | Manage Stakeholders | BM | S/C
[11 empty] | Monitor & Control | Manage Stakeholders | BIG | I
[11 empty] | Monitor & Control | Manage Stakeholders | SP | C
[11 empty] | Monitor & Control | Manage Stakeholders | PM | R
[11 empty] | Monitor & Control | Manage Stakeholders | PCT | I
[11 empty] | Monitor & Control | Manage Requirements | AGB | I
[11 empty] | Monitor & Control | Manage Requirements | PSC | I
[11 empty] | Monitor & Control | Manage Requirements | PO | A
[11 empty] | Monitor & Control | Manage Requirements | BM | C
[11 empty] | Monitor & Control | Manage Requirements | BIG | C
[11 empty] | Monitor & Control | Manage Requirements | SP | I
[11 empty] | Monitor & Control | Manage Requirements | PM | R
[11 empty] | Monitor & Control | Manage Requirements | PCT | S
[11 empty] | Monitor & Control | Manage Project Changes | AGB | I
[11 empty] | Monitor & Control | Manage Project Changes | PSC | C
[11 empty] | Monitor & Control | Manage Project Changes | PO | A
[11 empty] | Monitor & Control | Manage Project Changes | BM | S
[11 empty] | Monitor & Control | Manage Project Changes | BIG | I
[11 empty] | Monitor & Control | Manage Project Changes | SP | I
[11 empty] | Monitor & Control | Manage Project Changes | PM | R
[11 empty] | Monitor & Control | Manage Project Changes | PCT | C
[11 empty] | Monitor & Control | Manage Risks | AGB | I
[11 empty] | Monitor & Control | Manage Risks | PSC | C
[11 empty] | Monitor & Control | Manage Risks | PO | A
[11 empty] | Monitor & Control | Manage Risks | BM | S/C
[11 empty] | Monitor & Control | Manage Risks | BIG | C
[11 empty] | Monitor & Control | Manage Risks | SP | I
[11 empty] | Monitor & Control | Manage Risks | PM | R
[11 empty] | Monitor & Control | Manage Risks | PCT | C
[11 empty] | Monitor & Control | Manage Issues & Decisions | AGB | I
[11 empty] | Monitor & Control | Manage Issues & Decisions | PSC | I
[11 empty] | Monitor & Control | Manage Issues & Decisions | PO | A
[11 empty] | Monitor & Control | Manage Issues & Decisions | BM | S
[11 empty] | Monitor & Control | Manage Issues & Decisions | BIG | C
[11 empty] | Monitor & Control | Manage Issues & Decisions | SP | I
[11 empty] | Monitor & Control | Manage Issues & Decisions | PM | R
[11 empty] | Monitor & Control | Manage Issues & Decisions | PCT | C
[11 empty] | Monitor & Control | Manage Quality | AGB | I
[11 empty] | Monitor & Control | Manage Quality | PSC | I
[11 empty] | Monitor & Control | Manage Quality | PO | I
[11 empty] | Monitor & Control | Manage Quality | BM | S/C
[11 empty] | Monitor & Control | Manage Quality | BIG | C
[11 empty] | Monitor & Control | Manage Quality | SP | A
[11 empty] | Monitor & Control | Manage Quality | PM | R
[11 empty] | Monitor & Control | Manage Quality | PCT | C
[11 empty] | Monitor & Control | Manage Deliverables Acceptance | AGB | I
[11 empty] | Monitor & Control | Manage Deliverables Acceptance | PSC | I
[11 empty] | Monitor & Control | Manage Deliverables Acceptance | PO | A
[11 empty] | Monitor & Control | Manage Deliverables Acceptance | BM | S
[11 empty] | Monitor & Control | Manage Deliverables Acceptance | BIG | C
[11 empty] | Monitor & Control | Manage Deliverables Acceptance | SP | C
[11 empty] | Monitor & Control | Manage Deliverables Acceptance | PM | R
[11 empty] | Monitor & Control | Manage Deliverables Acceptance | PCT | C
[11 empty] | Monitor & Control | Manage Business Implementation | AGB | I
[11 empty] | Monitor & Control | Manage Business Implementation | PSC | I
[11 empty] | Monitor & Control | Manage Business Implementation | PO | A
[11 empty] | Monitor & Control | Manage Business Implementation | BM | R
[11 empty] | Monitor & Control | Manage Business Implementation | BIG | C
[11 empty] | Monitor & Control | Manage Business Implementation | SP | I
[11 empty] | Monitor & Control | Manage Business Implementation | PM | S
[11 empty] | Monitor & Control | Manage Business Implementation | PCT | I
[11 empty] | Monitor & Control | Manage Transition | AGB | I
[11 empty] | Monitor & Control | Manage Transition | PSC | A
[11 empty] | Monitor & Control | Manage Transition | PO | C
[11 empty] | Monitor & Control | Manage Transition | BM | C
[11 empty] | Monitor & Control | Manage Transition | BIG | C
[11 empty] | Monitor & Control | Manage Transition | SP | C
[11 empty] | Monitor & Control | Manage Transition | PM | R
[11 empty] | Monitor & Control | Manage Transition | PCT | C
[11 empty] | Monitor & Control | Manage Outsourcing | AGB | A
[11 empty] | Monitor & Control | Manage Outsourcing | PSC | C
[11 empty] | Monitor & Control | Manage Outsourcing | PO | C
[11 empty] | Monitor & Control | Manage Outsourcing | BM | C
[11 empty] | Monitor & Control | Manage Outsourcing | BIG | I
[11 empty] | Monitor & Control | Manage Outsourcing | SP | S
[11 empty] | Monitor & Control | Manage Outsourcing | PM | R
[11 empty] | Monitor & Control | Manage Outsourcing | PCT | I
[11 empty] | Closing | Project-End Review Meeting | AGB | I
[11 empty] | Closing | Project-End Review Meeting | PSC | A
[11 empty] | Closing | Project-End Review Meeting | PO | C
[11 empty] | Closing | Project-End Review Meeting | BM | S
[11 empty] | Closing | Project-End Review Meeting | BIG | C
[11 empty] | Closing | Project-End Review Meeting | SP | C
[11 empty] | Closing | Project-End Review Meeting | PM | R
[11 empty] | Closing | Project-End Review Meeting | PCT | C
[11 empty] | Closing | Project-End Report | AGB | I
[11 empty] | Closing | Project-End Report | PSC | A
[11 empty] | Closing | Project-End Report | PO | C
[11 empty] | Closing | Project-End Report | BM | S
[11 empty] | Closing | Project-End Report | BIG | C
[11 empty] | Closing | Project-End Report | SP | C
[11 empty] | Closing | Project-End Report | PM | R
[11 empty] | Closing | Project-End Report | PCT | C
[11 empty] | Closing | Administrative Closure | AGB | I
[11 empty] | Closing | Administrative Closure | PSC | C
[11 empty] | Closing | Administrative Closure | PO | A
[11 empty] | Closing | Administrative Closure | BM | C
[11 empty] | Closing | Administrative Closure | BIG | I
[11 empty] | Closing | Administrative Closure | SP | C
[11 empty] | Closing | Administrative Closure | PM | R
[11 empty] | Closing | Administrative Closure | PCT | I

## rasci_codes
rasci | name | description
n.a. | Not Applicable | NULL
R | Responsible | Does the work. Others can be asked to assist in a supporting role. There is just one responsible person for any given task.
A | Accountable | Ultimately answerable for the correct and thorough completion of the work. There is just one accountable person for any given task.
S | Supports | As part of a team, roles with a support function work with the person responsible. The support role helps complete the task.
C | Consulted | Those whose opinions are requested and with whom there is two-way communication. The consulted role does not help complete the task.
I | Informed | Those who are kept informed of progress.
A/S | Accountable/Supports | NULL
S/C | Supports/Consulted | NULL
I/C | Informed/Consulted | NULL

## rasci
id_artefact | id_role | rasci
0 | AGB | I
0 | PSC | n.a.
0 | PO | A/S
0 | BM | R
0 | BIG | S/C
0 | SP | I
0 | PM | n.a.
0 | PCT | n.a.
1 | AGB | I
1 | PSC | C
1 | PO | A
1 | BM | R
1 | BIG | C
1 | SP | S
1 | PM | S
1 | PCT | n.a.
2 | AGB | I
2 | PSC | A
2 | PO | C
2 | BM | S
2 | BIG | C
2 | SP | S
2 | PM | R
2 | PCT | C
3 | AGB | I
3 | PSC | A
3 | PO | C
3 | BM | S
3 | BIG | C
3 | SP | C
3 | PM | R
3 | PCT | C
4 | AGB | I
4 | PSC | I
4 | PO | A
4 | BM | S
4 | BIG | C
4 | SP | I
4 | PM | R
4 | PCT | C
5 | AGB | I
5 | PSC | I
5 | PO | A
5 | BM | S
5 | BIG | C
5 | SP | I
5 | PM | R
5 | PCT | C
6 | AGB | I
6 | PSC | A
6 | PO | C
6 | BM | S/C
6 | BIG | C
6 | SP | C
6 | PM | R
6 | PCT | S/C
7 | AGB | A
7 | PSC | C
7 | PO | C
7 | BM | C
7 | BIG | I
7 | SP | S
7 | PM | R
7 | PCT | I
8 | AGB | I
8 | PSC | A
8 | PO | C
8 | BM | S
8 | BIG | I
8 | SP | C
8 | PM | R
8 | PCT | C
9 | AGB | I
9 | PSC | A
9 | PO | C
9 | BM | C
9 | BIG | C
9 | SP | C
9 | PM | R
9 | PCT | C
10 | AGB | I
10 | PSC | I
10 | PO | A
10 | BM | R
10 | BIG | C
10 | SP | I
10 | PM | S
10 | PCT | I
12 | AGB | I
12 | PSC | I
12 | PO | A
12 | BM | C
12 | BIG | C
12 | SP | I
12 | PM | R
12 | PCT | S
13 | AGB | I
13 | PSC | I
13 | PO | A
13 | BM | C
13 | BIG | I
13 | SP | I
13 | PM | R
13 | PCT | I
14 | AGB | I
14 | PSC | C
14 | PO | A
14 | BM | C
14 | BIG | I
14 | SP | I
14 | PM | R
14 | PCT | I
15 | AGB | I
15 | PSC | I
15 | PO | A
15 | BM | C
15 | BIG | C
15 | SP | I
15 | PM | R
15 | PCT | C
16 | AGB | I
16 | PSC | A
16 | PO | C
16 | BM | C
16 | BIG | C
16 | SP | C
16 | PM | R
16 | PCT | C
17 | AGB | I
17 | PSC | I
17 | PO | A
17 | BM | S
17 | BIG | C
17 | SP | I
17 | PM | R
17 | PCT | C
18 | AGB | I
18 | PSC | A
18 | PO | C
18 | BM | S/C
18 | BIG | C
18 | SP | C
18 | PM | R
18 | PCT | C
19 | AGB | I
19 | PSC | I
19 | PO | A
19 | BM | S
19 | BIG | I
19 | SP | I
19 | PM | R
19 | PCT | I
20 | AGB | I
20 | PSC | I
20 | PO | I
20 | BM | S
20 | BIG | C
20 | SP | I
20 | PM | A
20 | PCT | R
21 | AGB | I
21 | PSC | I
21 | PO | A
21 | BM | S/C
21 | BIG | I/C
21 | SP | I/C
21 | PM | R
21 | PCT | C
22 | AGB | I
22 | PSC | I
22 | PO | A
22 | BM | C
22 | BIG | I
22 | SP | I
22 | PM | R
22 | PCT | C
23 | AGB | I
23 | PSC | I
23 | PO | A
23 | BM | C
23 | BIG | C
23 | SP | I
23 | PM | R
23 | PCT | C
24 | AGB | I
24 | PSC | I
24 | PO | A
24 | BM | C
24 | BIG | C
24 | SP | I
24 | PM | R
24 | PCT | C
25 | AGB | I
25 | PSC | I
25 | PO | A
25 | BM | C
25 | BIG | C
25 | SP | I
25 | PM | R
25 | PCT | C
26 | AGB | I
26 | PSC | I
26 | PO | A
26 | BM | S/C
26 | BIG | I
26 | SP | C
26 | PM | R
26 | PCT | I
27 | AGB | I
27 | PSC | I
27 | PO | A
27 | BM | C
27 | BIG | C
27 | SP | I
27 | PM | R
27 | PCT | S
28 | AGB | I
28 | PSC | C
28 | PO | A
28 | BM | S
28 | BIG | I
28 | SP | I
28 | PM | R
28 | PCT | C
29 | AGB | I
29 | PSC | C
29 | PO | A
29 | BM | S/C
29 | BIG | C
29 | SP | I
29 | PM | R
29 | PCT | C
30 | AGB | I
30 | PSC | I
30 | PO | A
30 | BM | S
30 | BIG | C
30 | SP | I
30 | PM | R
30 | PCT | C
31 | AGB | I
31 | PSC | I
31 | PO | I
31 | BM | S/C
31 | BIG | C
31 | SP | A
31 | PM | R
31 | PCT | C
32 | AGB | I
32 | PSC | I
32 | PO | A
32 | BM | S
32 | BIG | C
32 | SP | C
32 | PM | R
32 | PCT | C
33 | AGB | I
33 | PSC | I
33 | PO | A
33 | BM | R
33 | BIG | C
33 | SP | I
33 | PM | S
33 | PCT | I
34 | AGB | I
34 | PSC | A
34 | PO | C
34 | BM | C
34 | BIG | C
34 | SP | C
34 | PM | R
34 | PCT | C
35 | AGB | A
35 | PSC | C
35 | PO | C
35 | BM | C
35 | BIG | I
35 | SP | S
35 | PM | R
35 | PCT | I
36 | AGB | I
36 | PSC | A
36 | PO | C
36 | BM | S
36 | BIG | C
36 | SP | C
36 | PM | R
36 | PCT | C
37 | AGB | I
37 | PSC | A
37 | PO | C
37 | BM | S
37 | BIG | C
37 | SP | C
37 | PM | R
37 | PCT | C
38 | AGB | I
38 | PSC | C
38 | PO | A
38 | BM | C
38 | BIG | I
38 | SP | C
38 | PM | R
38 | PCT | I

## phases
id_phase | code | name | description
0 | initiating | Initiating | Define the desired outcomes. Create a Business Case. Define the project scope. Get the project off to a good start.
1 | planning | Planning | Assign the Project Core Team (PCT). Elaborate the project scope. Plan the work.
2 | executing | Executing | Coordinate the execution of project plans. Produce deliverables.
3 | closing | Closing | Coordinate formal acceptance of the project. Report on project performance. Capture Lessons Learned and post-project recommendations. Close the project administratively.
4 | monitorAndControl | Monitor & Control | Oversee all project work and management activities over the duration of the project: monitor project performance, measure progress, manage changes, address risks and issues, identify corrective actions etc.

## artefacts
id_artefact | code | name | id_phase | description
0 | projectInitiationRequest | Project Initiation Request | 0 | NULL
1 | businessCase | Business Case | 0 | NULL
2 | projectCharter | Project Charter | 0 | NULL
3 | planningKickoffMeeting | Planning Kick-off Meeting | 1 | NULL
4 | projectHandbook | Project Handbook | 1 | NULL
5 | projectStakeholderMatrix | Project Stakeholder Matrix | 1 | NULL
6 | projectWorkPlan | Project Work Plan | 1 | NULL
7 | outsourcingPlan | Outsourcing Plan | 1 | NULL
8 | deliverablesAcceptancePlan | Deliverables Acceptance Plan | 1 | NULL
9 | transitionPlan | Transition Plan | 1 | NULL
10 | businessImplementationPlan | Business Implementation Plan | 1 | NULL
11 | managementPlans | Management Plans | 1 | NULL
12 | requirementsManagementPlan | Requirements Management Plan | 1 | NULL
13 | projectChangeManagementPlan | Project Change Management Plan | 1 | NULL
14 | riskManagementPlan | Risk Management Plan | 1 | NULL
15 | issueManagementPlan | Issue Management Plan | 1 | NULL
16 | qualityManagementPlan | Quality Management Plan | 1 | NULL
17 | communicationsManagementPlan | Communications Management Plan | 1 | NULL
18 | executingKickoffMeeting | Executing Kick-off Meeting | 2 | NULL
19 | projectCoordination | Project Coordination | 2 | NULL
20 | qualityAssurance | Quality Assurance | 2 | NULL
21 | projectReporting | Project Reporting | 2 | NULL
22 | informationDistribution | Information Distribution | 2 | NULL
23 | monitorProjectPerformance | Monitor Project Performance | 4 | NULL
24 | controlSchedule | Control Schedule | 4 | NULL
25 | controlCost | Control Cost | 4 | NULL
26 | manageStakeholders | Manage Stakeholders | 4 | NULL
27 | manageRequirements | Manage Requirements | 4 | NULL
28 | manageProjectChanges | Manage Project Changes | 4 | NULL
29 | manageRisks | Manage Risks | 4 | NULL
30 | manageIssuesAndDecisions | Manage Issues & Decisions | 4 | NULL
31 | manageQuality | Manage Quality | 4 | NULL
32 | manageDeliverablesAcceptance | Manage Deliverables Acceptance | 4 | NULL
33 | manageBusinessImplementation | Manage Business Implementation | 4 | NULL
34 | manageTransition | Manage Transition | 4 | NULL
35 | manageOutsourcing | Manage Outsourcing | 4 | NULL
36 | projectEndReviewMeeting | Project-End Review Meeting | 3 | NULL
37 | projectEndReport | Project-End Report | 3 | NULL
38 | administrativeClosure | Administrative Closure | 3 | NULL

## RASCI_roles
id_role | name | description
AGB | Appropriate Governance Body
PSC | Project Steering Committee
PO | Project Owner
BM | Business Manager
BIG | Business Implementation Group
SP | Solution Provider
PM | Project Manager
PCT | Project Core Team